## HIPAA_RISK_ASSESSMENT_REGISTRY
RISK ID | HIPAA DOMAIN | HIPAA RULE/CITATION STANDARD | RISK DESCRIPTION STATEMENT | LIKELIHOOD (1-5) | IMPACT (1-5) | INHERENT RISK SCORE | RISK RATING | REMEDIATION/MITIGATION | OWNER | STATUS | TARGET COMPLETION
RISK-001 | Technical Safeguards | 164.312(a)(2)(iv) -encryption | ePHI transmitted across public network without encryption | 4 | 5 | 20 | HIGH | Enforce TLS 1.3 across all endpoints and deprecate legacy SSL protocols | Dev0ps lead | InProgress | 2026-08-28
RISK-002 | Administrative Safeguards | 164.308 (a)(1)(ii)(B)-RISK | Third-party vendors handling | 3 | 4 | 12 | MEDIUM | Conduct vendor audit; request signed BAAs from all active software vendors accessing ePHI | Compliance Officer | Open | 2026-09-04
RISK003 | Physical Safeguards | 164.310(d)(1) -Device Controls | Laptops used by remote staff lack central full-disk encryption (BitLocker/FileVault) | 3 | 5 | 15 | HIGH | Deploy MDM policy enforcing mandatory BitLocker/FileVault encryption across all devices | IT Admin | In Progress | 2026-08-21